## Sprint 1
Sprint Backlog - Sprint 1 (Final)
Work Item / Task | Owner | Est. Effort | Status
PBI 5.1: Category Management | Tian | 16h | To Do
Task: Build category list page with columns status badge and actions +1 | Tian | 4h | To Do
Task: Create APIs for category list create edit status and delete +1 | Xian | 5h | To Do
Task: Add validation for empty trim unique and inactive rule +1 | Tian | 3h | To Do
Task: Connect category page with APIs and refresh results +1 | Xian | 4h | To Do
PBI 5.2: Tag Management | Xian | 16h | To Do
Task: Build tag list page and create edit delete UI +1 | Tian | 4h | To Do
Task: Create APIs for tag CRUD and soft delete +1 | Xian | 4h | To Do
Task: Add validation for empty trim unique and inactive rule +1 | Tian | 3h | To Do
Task: Implement tag merge and deduplicated link migration after core stable +2 | Xian | 5h | To Do
PBI 5.3: Resource Lifecycle Management | Xian | 18h | To Do
Task: Implement archive unpublish and restore APIs +1 | Xian | 5h | To Do
Task: Add single and bulk lifecycle actions in admin UI +1 | Tian | 5h | To Do
Task: Add resource category checks and status history recording +2 | Xian | 5h | To Do
Task: Connect status badges confirmations and error feedback +1 | Tian | 3h | To Do
PBI 5.4: Resource Administration Page | Tian | 16h | To Do
Task: Build unified admin resource list page for admin actions +1 | Tian | 5h | To Do
Task: Add keyword category tag and status filters +1 | Tian | 4h | To Do
Task: Add creator and created date range filters with query API +1 | Xian | 4h | To Do
Task: Connect row actions bulk selection and refresh filtered results +1 | Xian | 3h | To Do
PBI 5.5: Reporting Dashboard | Tian | 12h | To Do
Task: Build summary cards and reporting table UI +1 | Tian | 4h | To Do
Task: Create APIs for resource status category and tag counts +1 | Xian | 4h | To Do
Task: Add data mapping empty state handling and basic status chart +1 | Tian | 2h | To Do
Task: Verify workflow counts against resource tag and category data +1 | Xian | 2h | To Do
Sprint Quality Assurance Across all PBIs | All | 8h | To Do
Task: Unit testing for validation rules and lifecycle flows +2 | Xian | 4h | To Do
Task: Manual testing and frontend backend integration check +2 | Tian | 4h | To Do
Legend: +1 = moderate complexity; +2 = higher complexity / stretch-risk

## Change Summary
Section | Original version | Revised version | Why I changed it
Title | Sprint Backlog - Sprint 1 | Sprint Backlog - Sprint 1 (Final) | Marked the workbook as the reviewed/final version.
PBI 5.1 / Task 1 | Build category list page with columns and actions +1 | Build category list page with columns status badge and actions +1 | Added 'status badge' because Category Management should visibly show active/inactive state.
PBI 5.1 / Task 2 | Create APIs for list create edit status and delete +1 | Create APIs for category list create edit status and delete +1 | Made the API wording explicit so it is clearly category-specific.
PBI 5.1 / Task 4 | Add category resource view with keyword and status filters +1 | Connect category page with APIs and refresh results +1 | Kept Sprint 1 focused on category management MVP instead of mixing in a resource view.
PBI 5.2 / Task 3 | Implement tag merge and deduplicated link migration +1 | Implement tag merge and deduplicated link migration after core stable +2 | Raised complexity and pushed it after the core because tag merge is more advanced than CRUD.
PBI 5.2 / Task 4 | Add tag resource view with keyword and status filters +1 | Add validation for empty trim unique and inactive rule +1 | Replaced resource-view scope with core validation to keep Tag Management aligned with Category Management.
PBI 5.3 / Task 1 | Implement archive unpublish publish restore APIs +1 (6h) | Implement archive unpublish and restore APIs +1 (5h) | Removed publish because it may overlap with review/publication workflow; kept unpublish explicit and slightly reduced effort.
PBI 5.3 / Task 3 | Add category checks and status history recording +1 (4h) | Add resource category checks and status history recording +2 (5h) | Clarified the task and increased complexity/effort because status-history logic is heavier.
PBI 5.4 / Task 1 | Build unified admin resource list page +1 | Build unified admin resource list page for admin actions +1 | Clarified that this page is specifically for admin operations, not public discovery.
PBI 5.4 / Task 3 | Add created by date range filters and query API +1 | Add creator and created date range filters with query API +1 | Made the filter wording clearer and more explicit.
PBI 5.4 / Task 4 | Connect list actions and refresh filtered results +1 | Connect row actions bulk selection and refresh filtered results +1 | Added bulk selection because it fits lifecycle actions in admin pages.
PBI 5.5 / Task 2 | Create APIs for status category and tag counts +1 | Create APIs for resource status category and tag counts +1 | Made reporting explicitly status-based so the dashboard reflects workflow.
PBI 5.5 / Task 3 | Add data mapping and empty state handling +1 | Add data mapping empty state handling and basic status chart +1 | Added a simple status chart to strengthen the reporting dashboard.
PBI 5.5 / Task 4 | Verify counts against resource tag and category data +1 | Verify workflow counts against resource tag and category data +1 | Changed verification wording to emphasize workflow/status counts.
QA / Task 1 | Unit testing for validation rules and status flows +2 | Unit testing for validation rules and lifecycle flows +2 | Aligned wording with Resource Lifecycle Management.
Legend | (none) | Legend: +1 = moderate complexity; +2 = higher complexity / stretch-risk | Added a legend because you wanted to keep +1/+2 notation.